## Sheet1
			Restaurant: Truffle POS
Bug Id	Bug modules	Sub modules	Bug description	Attechments	Bug Date	Assign to Developer
1	My Profile	Web Edit Profile	First name and last name field accept Special character / If we are enter contact number accept only 2, 3 and 6 digit / In username accept digit also	TF1.png
2	User Role Management	New Record	If we field Shold New record module and action then click button but not showing User role managment page(Action column)	TF2.png
3	Notification Management	Add Notification>Specific User	Send notification To limits more than 50 characters	TF5.png
4	Investory Management	Add Notification	Starting Quantity , minimum Quantity, Item On hand digit limit not set / Also price limit not set>more then 6 digit	TF6.png
5	User Management	Employeee	Employe Payroll Deatils >Staff rate>No limits in digit	TF7.png
6	User Management	Employeee	Select Branch two times Show	TF8.png
7	Menu Management	Add Serving	Serving Size name>accept special charcter
8	Menu Management	Advertise	Add Advertise> In Advertise name Accept special charcater
9	Menu Management	Menu categoty	Add Menu Category> Serving Size leval>limit not set
10	Departments	Add Department	Restaurant Branch Name>no limit sets
11	Product and Item	Add Menu item	when we put veg pizza in sub category and then fill all details then click on submit button > non veg symbol show in mobile application
12	Inventory Management	Add Inventory	Item Quantity, minimum Quantity,Item on hand digit limit not set
13

## Sheet2
			Restaurant: Truffle Dev
Bug Id	Bug modules	Sub modules	Bug description	Attechments	Bug Date	Assign to Developer
1	My Profile	Web Edit Profile	First name and last name field accept Special character and digit / If we are enter contact number accept only 2, 3 and 6 digit / In username accept digit also
2	Cart	Bill Details	Add 4 item and all total 160.99 but sub total show 162.99>calculation not proper
3	My Profile	Change Password	Current Password filed colour not Proper	TD1.png
4	Drawer menu> My Profile	Edit Profile	Suggestion >Add photo > Replace buttone Cancel to Remove option / And Profile Pic not Remove / Not show full profile
5	Cart		Price amount alignments not proper
	Poduct and item	Select category	New Category >Accept digit in name field

## Sheet3
			Restaurant: Truffle stg
Bug Id	Bug modules	Sub modules	Bug description	Attechments	Bug Date	Assign to Developer
1	Poduct and item	Select category	New Category >Accept digit in name field
2	Promotions	Diwali	Edit Promotion >Discount Price >Accept (-) minus digit
3	Menu Category	Edit Menu Category	Applicable time period >Date range > Start date Start 1914	Tfstg5.png
4	Menu Sub category	Edit Menu Sub Category	Applicable time period>Date Range > Showing The Specific date And End date in place of start date and end date	Tfstg6.png
5	Promotion	Promotion Name And Coupon Code	Accept Special Character	TfStg7.png
6	Promotion	Add Promotion	In Use of coupon code validation not proper (not add code )	Tfstg8.png
7	Promotions	Add Promotion	Coupon Code> place holder text not proper (Enter Coupon code )	TfStg9.png
8	Product and Item	Serving Size	Missing * icon	Tfstg10.png
9	Product and Item	Menu name	If we enter Menu name field then automatically same kitchen Print name field
10	Product and Item	Add Menu	Kitchen Printer place holder text not same S is missing
11	Menu Category	Add Menu Category	In Category Image Validation> S and I is not Capital	Tfstg11.png
13	Special /combos		View All not showing in Specials /combos
14	Refund Report	Tender Option	If we select By Tender type and Select any Tender Type>Tender type Alignments not proper	Tfstg13.png